## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | I want to upload Python/Java files so that they can be analyzed. | Must Have | None | Sanjana | Completed
Sprint 1 | Sprint 1 | US002 | I want to detect file language and validate syntax. | Must Have | US001 | Sanjana | Completed
Sprint 2 | Sprint 2 | US003 | I want to load OWASP standards into FAISS vector store via RAG pipeline. | Must Have | None | Sanjana | Completed
Sprint 2 | Sprint 2 | US004 | I want code smell & design anti-pattern detection for Python/Java. | Must Have | US002 | Sanjana | Completed
Sprint 3 | Sprint 3 | US005 | I want OWASP vulnerability scanning (SQLi, XSS, Secrets). | Must Have | US002 | Sanjana | Completed
Sprint 3 | Sprint 3 | US006 | I want automated remediation suggestions with fixed code snippets. | Should Have | US004, US005 | Sanjana | Completed
Sprint 4 | Sprint 4 | US007 | I want PR summary review reports generated and exportable. | Must Have | US004, US005 | Sanjana | Completed
Sprint 4 | Sprint 4 | US008 | I want a RAG-powered Conversational Code Assistant interface. | Could Have | US003 | Sanjana | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 86 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | TSK-01 | Implement Code Upload & file extension validation UI/backend | 2026-07-06 | 2026-07-08 | Sanjana | Development | Completed | 8 | Day 1: 4; Day 2: 4; Day 3: 0; Day 4: 0; Day 5: 0
US002 | TSK-02 | Build programming language detection logic (Python/Java) | 2026-07-08 | 2026-07-10 | Sanjana | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 4; Day 4: 4; Day 5: 0
US002 | TSK-03 | Set up syntax validation parsers & error handling | 2026-07-11 | 2026-07-13 | Sanjana | Development | Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 3
US003 | TSK-04 | Process OWASP standards PDF & chunk documents | 2026-07-14 | 2026-07-15 | Sanjana | Development | Completed | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US003 | TSK-05 | Generate text embeddings & index into FAISS database | 2026-07-16 | 2026-07-17 | Sanjana | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US004 | TSK-06 | Develop Code Analysis Agent (AST traversal, code smells, complexity) | 2026-07-17 | 2026-07-19 | Sanjana | Development | Completed | 12 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US005 | TSK-07 | Develop Security Vulnerability Agent (SQLi, Secret scanning, XSS) | 2026-07-20 | 2026-07-22 | Sanjana | Development | Completed | 12 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US006 | TSK-08 | Build Remediation Agent for code fix suggestions | 2026-07-22 | 2026-07-24 | Sanjana | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US007 | TSK-09 | Develop PR Summary Agent & exportable report generator | 2026-07-25 | 2026-07-27 | Sanjana | Development | Completed | 8 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
US008 | TSK-10 | Implement RAG Conversational Code Assistant UI & agent integration | 2026-07-27 | 2026-07-30 | Sanjana | Development | Completed | 10 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Unsupported file upload format crash | Added file type restriction validation
Sprint 1 | Day 4 | Language detection ambiguity on Java syntax | Refined pattern matching rules
Sprint 2 | Day 2 | Duplicate document chunking in RAG pipeline | Adjusted text splitter chunk size and overlap
Sprint 2 | Day 4 | Duplicate vector embeddings stored in FAISS | Added deduplication filter before insertion
Sprint 3 | Day 2 | AST traversal skipping nested functions in code analysis | Updated recursive AST visitor logic
Sprint 3 | Day 4 | SQL injection regex missing string concatenation | Expanded regex rule pattern for dynamic SQL

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-06 | 2026-07-12 | Sanjana | Automated edge-case input unit testing | Manual file payload validation | Daily commit discipline | Created comprehensive unit test cases for file upload
2 | Sprint 2 | 2026-07-13 | 2026-07-19 | Sanjana | Vector store indexing validation scripts | Hardcoding vector chunk sizes | Detailed AST analysis prototyping | Optimized RAG chunking parameters
3 | Sprint 3 | 2026-07-20 | 2026-07-26 | Sanjana | AST rule coverage expansion for Java | Relying on single regex patterns for security | Granular defect logging | Enhanced security pattern engine
4 | Sprint 4 | 2026-07-27 | 2026-08-02 | Sanjana | End-to-end integration test execution | Delaying report styling cleanup | Frequent retrospectives | Finalized multi-agent orchestrator pipeline
5
6
7