## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D001 | Sanjana | 2026-07-10 | System accepted unsupported .txt files | Code Upload | Sanjana | File validation missing | Added file type validation | 2026-07-10 | Closed
D002 | Sanjana | 2026-07-13 | Java source detected as Python | Language Detection | Sanjana | Detection logic incomplete | Improved language detection rules | 2026-07-14 | Closed
D003 | Sanjana | 2026-07-15 | Empty file caused application crash | Syntax Validation | Sanjana | Null input not handled | Added empty file validation | 2026-07-15 | Closed
D004 | Sanjana | 2026-07-15 | Invalid Python syntax not reported correctly | Syntax Validation | Sanjana | Exception handling issue | Improved parser exception handling | 2026-07-15 | Closed
D005 | Sanjana | 2026-07-16 | Duplicate OWASP document chunks generated | RAG Pipeline | Sanjana | Chunk overlap configuration | Optimized chunk size and overlap | 2026-07-16 | Closed
D006 | Sanjana | 2026-07-17 | Duplicate embeddings stored | FAISS Database | Sanjana | Duplicate insertion logic | Added duplicate check | 2026-07-16 | Closed
D007 | Sanjana | 2026-07-18 | Long Method detection missed nested functions | Code Analysis Agent | Sanjana | AST traversal incomplete | Updated AST traversal | 2026-07-18 | Closed
D008 | Sanjana | 2026-07-18 | Cyclomatic complexity calculated incorrectly | Code Analysis Agent | Sanjana | Missing branch conditions | Corrected complexity algorithm | 2026-07-19 | Closed
D009 | Sanjana | 2026-07-19 | Duplicate code reported multiple times | Code Analysis Agent | Sanjana | Duplicate reporting logic | Removed duplicate entries | 2026-07-19 | Closed
D010 | Sanjana | 2026-07-20 | SQL Injection false negative | Security Agent | Sanjana | Query concatenation pattern missed | Enhanced SQL detection rules | 2026-07-20 | Closed
D011 | Sanjana | 2026-07-21 | Hardcoded API keys not detected | Security Agent | Sanjana | Regex pattern incomplete | Updated secret detection regex | 2026-07-21 | Closed
D012 | Sanjana | 2026-07-22 | Remediation code snippet had missing imports | Remediation Agent | Sanjana | Logic defect | Added automatic import generation to fixes | 2026-07-22 | Closed | Verified
D013 | Sanjana | 2026-08-01 | PR Summary failed to render table layout on long inputs | PR Summary Agent | Sanjana | User Interface | Updated markdown table builder formatting | 2026-08-03 | Closed | Verified
D014 | Sanjana | 2026-08-04 | Conversational assistant context window exceeded limit | Conversational Assistant | Sanjana | Maintainability | Implemented context truncation and sliding window | 2026-08-08 | Closed | Verified
D015 | Sanjana | 2026-08-14 | Exported PDF report formatting misaligned on multi-page findings | Report Export | Sanjana | Standards | Adjusted page breakdown and margins in PDF generator | 2026-08-15 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others